## Sheet1
Sprint/Tasks | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27
First Prototype | bar: 2019-10-21 to 2019-11-18
Lock Scene | bar: 2019-10-21 to 2019-10-28
Parents Corner | bar: 2019-10-28 to 2019-11-04
Level Menu | bar: 2019-10-21 to 2019-11-04
Video Player | bar: 2019-10-21 to 2019-11-04
Unity Voice Recognition Demo | bar: 2019-11-04 to 2019-11-11
Scene Manager | bar: 2019-10-21 to 2019-10-28
Rewards Effects | bar: 2019-10-28 to 2019-11-11
Team Video | bar: 2019-11-11 to 2019-11-18
Demo Day | bar: 2019-11-25 to 2019-12-09
Get Spectrum Data and Buffers from Mic | bar: 2019-11-25 to 2019-12-02
Effects Scripting | bar: 2019-11-25
Team Contract / Report | bar: 2019-12-02 to 2019-12-09
Winter Break | bar: 2019-12-16 to 2020-01-13
Sync Level Menu with Videos/Database | bar: 2019-12-16 to 2020-01-13
Voice Envelope Processing | bar: 2019-12-16 to 2019-12-30
Effects Assets and Sync with Sound | bar: 2019-12-23 to 2020-01-06
Parents Corner Sync Progress | bar: 2019-12-23 to 2020-01-13
Second Prototype | bar: 2020-01-20 to 2020-02-10
Video Recorder | bar: 2020-01-20 to 2020-02-10
Optimize and Test for Mobile | bar: 2020-01-20 to 2020-02-03
Make Video Scene Automatic | bar: 2020-01-20 to 2020-01-27
Make Professional, Custom UI Elements | bar: 2020-01-20 to 2020-02-03
Plan for Testing with Sample Groups | bar: 2020-02-03 to 2020-02-10
Integrate Client Voice Algo/ Vowel Detection | bar: 2020-01-20 to 2020-02-10
Project Completion | bar: 2020-02-17 to 2020-03-23
Remaining Database/Syncing | bar: 2020-02-17 to 2020-03-02
Optimize/Refactor Previous Sprint Code | bar: 2020-02-17 to 2020-03-23
Test with ASD/nonverbal Children | bar: 2020-03-16 to 2020-03-23
ECE Day/Finalizing with Client | bar: 2020-03-30 to 2020-04-27
Make Code into Unity Editor Prefabs/Assets as Needed | bar: 2020-03-30 to 2020-04-20
Final Report | bar: 2020-04-20 to 2020-04-27
Gather Analytics from Testing | bar: 2020-04-06 to 2020-04-20